## Sheet1
Sprint 1
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 (Dinsdag) | Day 2 (Woensdag) | Day 3 (Donderdag | Day 4 (vrijdag)
User Story #4 | 12
Work item 4.1 |  | Jim Stam | Done | 7 | 3 | 3 | 0 | 0
Work item 4.2 |  | Jim Stam | Done | 5 | 2 | 2 | 0 | 1
Work item 4.3 |  | Jim Stam | Done | 1 | 0 | 3 | 0 | 0
User Story #5 | 20
Work item 5.1 |  | Anil Rosaria | Done | 7 | 3 | 3 | 0 | 0
Work item 5.2 |  | Jawed Balkhi | Done | 7 | 0 | 0 | 3 | 3
User Story #9 | 20
Work item 9.1 |  | Jim Stam | Done | 7 | 4 | 2 | 1 | 0
Work item 9.2 |  | Ali Jawanshir | Done | 1 | 0 | 0 | 0 | 1
Total |  |  |  | 35 | 12 | 13 | 4 | 5