## Blad1
Projectnaam | User story # | Work item # | Day 5 - remaining hours | Day 4 | Day 3 | Day 2 | Day 1
Sprint 2 | User story 1 | Work item 1.1 | 7 | 4 | 3 | 2 | 0 | Make sure you fill in "hours remaining"
Sprint 2 | User story 1 | Work item 1.2 | 7 | 6 | 4 | 2 | 0
Sprint 2 | User story 1 | Work item 1.3 | 5 | 2 | 2 | 1 | 0
Sprint 2 | User story 4 | Work item 4.1 | 3 | 1 | 1 | 0 | 0
Sprint 2 | User story 4 | Work item 4.2 | 3 | 2 | 1 | 0 | 0
Sprint 2 | User story 6 | Work item 6.1 | 5 | 2 | 1 | 0 | 0
Sprint 2 | User story 6 | Work item 6.2 | 5 | 2 | 1 | 0 | 0
Sprint 2 | User story 7 | Work item 7.1 | 1 | 1 | 0 | 0 | 0
Sprint 2 | User Story 13 | Work item 13.1 | 2 | 1 | 0 | 0 | 0
Sprint 2 | User Story 13 | Work item 13.2 | 2 | 1 | 0 | 0 | 0
|  | Ideal | 30 | 23 | 16 | 9 | 2
|  | Actual | 30 | 22 | 13 | 5 | 0