## Blad1
Projectnaam | User story # | Work item # | Day 5 - remaining hours | Day 4 | Day 3 | Day 2 | Day 1
Sprint 3 | User story 2 | Work item 2.1 | 1 | 1 | 1 | 1 | 0 | Make sure you fill in "hours remaining"
Sprint 3 | User story 2 | Work item 2.2 | 1 | 1 | 1 | 1 | 0
Sprint 3 | User story 2 | Work item 2.3 | 1 | 1 | 1 | 1 | 0
Sprint 3 | User story 3 | Work item 3.1 | 1 | 1 | 1 | 1 | 0
Sprint 3 | User story 3 | Work item 3.2 | 1 | 1 | 1 | 1 | 0
Sprint 3 | User story 8 | Work item 8.1 | 2 | 2 | 1 | 0 | 0
Sprint 3 | User story 10 | Work item 10.1 | 2 | 2 | 1 | 0 | 0
Sprint 3 | User story 10 | Work item 10.2 | 2 | 2 | 1 | 0 | 0
Sprint 3 | User Story 14 | Work item 14.1 | 1 | 1 | 1 | 1 | 0
Sprint 3 | User Story 14 | Work item 14.2 | 2 | 2 | 0 | 0 | 0
Sprint 3 | User Story 15 | Work item 15.1 | 6 | 4 | 2 | 0 | 0
Sprint 3 | User Story 15 | Work item 15.2 | 6 | 4 | 2 | 0 | 0
|  | Ideal | 30 | 23 | 16 | 9 | 2
|  | Actual | 30 | 22 | 13 | 6 | 0